## Sheet1
Capital Projects
Schedule Report
As of June 15, 2021
|  |  |  | Start | Projected | Bids | Bids
| Area | Project | Budget Amount | Date | Completion Date | Required | Received
FY 2020-21
| Parks | Stewart Hill Park | 50000 | ? | 2022-05-30 | Not spent |  | 2022
| Sewer |  | 10000 | ? | 2022-05-30
|  | Total FY 2020-21 | 60000
FY 2021-22
| Administrative | Old School Stair Repair and Ramp | 12000 | 2021-08-01 | 2022-03-30
| Administrative | Master Plan City Square | 10000 | 2021-07-01 | 2021-12-30
| Parks | Stewart Hill Park | 200000 | 2021-04-01 | 2022-07-22
| Roads | Sidewalk and Park Strip 400 South (600 East to 500 East) | 70000 | ? | ?
| Roads | 400 South Sidwalk Right of Way Acquisition | 65000 | ? | ?
| Roads | Sidewalk Repairs City-wide | 50000 | 2021-07-01 | 2022-06-30 | 5000 | Planning | 2021-12-30
| Roads | Sidwalk and Park Strip 400 South (500 East to 400 East) | 45000 | ? | ?
| Roads | Road Seal | 40000 | 2021-08-01 | Complete
| Roads | Sidewalk Identified by Paint | 1200 | 2021-07-01 | Complete
| Roads | Sidewalk Identified by Paint | 1200 | 2021-07-01 | Complete
| Sewer | New Shop | 120000 | 2022-02-01 | 2022-04-15
| Sewer | New Truck | 35000 | 2021-07-01 | Complete
| Water | Upgrade Lower Well | 200000 | 2021-06-01 | 2022-05-30
| Water | Upgrade Water Line Lower Well to River Heights Blvd | 90000 | 2021-08-15 | 2022-05-30
| Water | Lower Well Property Aquisition | 15000 | 2021-06-01 | 2021-12-31
954400